## Deployment overview
S.No | Milestones and Deliverables | Owner | OS Version | Resource Allocated | Completion date | Status | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  | Akhila | 2024-07-11 | Completed
2 | Log Collector - Location 1 (Phoenix) | Client & BluSapphire | Rocky linux 8.7 minimal | Akhila | 2024-07-12 | Completed
3 | Sensor | Client & BluSapphire |  | Akhila | On-Hold | On-Hold | Currently on hold from client end as they dont as they dont have extra required port available and also have concern on network bandwidth.
4 | Responder | Client & BluSapphire | Windows server 2016 & above | Akhila | 2024-09-20 | Completed
5 | End to end integration test | BluSapphire |  | Akhila | 2024-07-12 | Completed
6 | Change Management Process If any | Client/BluSapphire | NA | NA | NA | NA
S.No | Milestones and Deliverables | Owner | OS Version | Resource Allocated | Completion date | Status | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  | Akhila | 2024-09-02 | Completed
2 | Log Collector - Location 2 (Bangalore or Cochin) | Client & BluSapphire | Rocky linux 8.7 minimal | Akhila | 2024-09-19 | Completed
3 | Sensor | Client & BluSapphire |  | Akhila | On-Hold | On-Hold | Currently on hold from client end as they dont as they dont have extra required port available and also have concern on network bandwidth.
4 | Responder | Client & BluSapphire | Windows server 2016 & above | Akhila | 2024-09-24 | Completed
5 | End to end integration test | BluSapphire |  | Akhila | 2024-09-19 | Completed
6 | Change Management Process If any | Client/BluSapphire | NA | NA | NA | NA

## Deployment details
S.No | Milestones and Deliverables | Owner | Planned Date | Planned Duration | Resource Allocated | Actual Start Date | Actual Duration | Completion date | Status | Agreed by Client | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  |  | Akhila |  |  | 2024-07-11 | Completed
1.1 | Add Organisation | BluSapphire |  |  | Akhila |  |  | 2024-07-11 | Completed
1.2 | Create S3 access | BluSapphire |  |  | Akhila |  |  | 2024-07-11 | Completed
1.3 | Admin User Account creation | BluSapphire |  |  | Akhila |  |  | 2024-07-11 | Completed
1.4 | Adding Devices | BluSapphire |  |  | Akhila |  |  | 2024-07-11 | Completed
2 | Log Collector - Location 1 (Phoenix) | Client & BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed
2.1 | Point of contact (at this Location) : Name & contact | Client |  |  | Akhila |  |  | 2024-07-12 | Completed
2.2 | Configuration Requirements (Basic): OS version: Rocky Linux 8.6 Minimal/Rocky Linux 8.7 Minimal only Hardware: vCPUs = 4 ; RAM = 8GB ; Disk space = 256 (min 200GB for '/opt' or '/' partition). | Client |  |  | Akhila |  |  | 2024-07-12 | Completed
2.3 | Is an Private Static IP address provisioned for the Log Collector(s), If so, specify the following for each Log Collector? | Client |  |  | Akhila |  |  | 2024-07-12 | Completed
2.4 | Is Internet provisioned on Log Collector during deployment activity? | Client |  |  | Akhila |  |  | 2024-07-12 | Completed
2.5 | Requested outbound ports to be opened on the firewall 5414, 5415 & 5416/udp to Master, BL ips and 443 port is opened | Client |  |  | Akhila |  |  | 2024-07-12 | Completed
2.6 | Installation of Log Collector software | Client/BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed |  | Dependency on 2.1 to 2.4
2.7 | Verification of Log Collector | Client/BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed |  | Dependency on 2.1 to 2.4
2.8 | Verify end to end connectivity with SaaS | Client/BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed |  | Dependency on 2.1 to 2.4
3 | Responder - Location 1 (Phoenix) | Client & BluSapphire |  |  | Akhila |  |  | 2024-09-20 | Completed
3.1 | Is an Private Static IP address provisioned for the Responder(s), If so, specify the following for each Responder machine? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.2 | Requested outbound ports to be opened on the firewall | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.3 | Is a service account created on AD for Responder machine with local admin privileges on endpoints? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.4 | Is WinRM setup in Group Policy on AD? And is responder machine part of WinRM client->trusted host list. | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.5 | Is the PowerShell version on Responder > 5.0? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.6 | Is the PowerShell version on all endpoints >= 3.0? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.7 | Is Responder and work-stations added in AD? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.8 | Is forward lookup and reverse lookup configured in active directory? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.9 | If there is any firewall running in workstations, need to enable inbound rule to allow WinRM and WMI. | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.10. | Is the Windows Firewall on Responder have the WinRM ports allowed? | Client |  |  | Akhila |  |  | 2024-09-20 | Completed
3.11 | Installation of Responder software | BluSapphire |  |  | Akhila |  |  | 2024-09-20 | Completed |  | Dependency on system requirements(H/W & S/W) and 5.1 & 5.4
3.12 | Configuration of Responder | BluSapphire |  |  | Akhila |  |  | 2024-09-20 | Completed |  | Dependency on 5.1 to 5.9
3.13 | Verification of Responder | BluSapphire |  |  | Akhila |  |  | 2024-09-20 | Completed |  | Dependency on 5.1 to 5.9
4 | MicroAgent Deployment at Windows End points | Client & BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed |  | Dependency on Log Collector
4.1 | MicroAgent build package and installation guide(GPO) to be provided | BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed
4.2 | Log forwarder (Winlogbeat) | Client/BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed
4.3 | Sysmon (Latest sysmon version to be downloaded from Microsoft Sysinternals website) | Client/BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed
4.4 | End to end communication check between MicroAgent & Log Collector | Client/BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed
5 | End to end integration test | BluSapphire |  |  | Akhila |  |  | 2024-07-12 | Completed |  | Dependency on 1 to 3
6 | Change Management Process If any | Client/BluSapphire
S.No | Milestones and Deliverables | Owner | Planned Date | Planned Duration | Resource Allocated | Actual Start Date | Actual Duration | Completion date | Status | Agreed by Client | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  |  | Akhila |  |  | 2024-09-02 | Completed
1.1 | Add Organisation | BluSapphire |  |  | Akhila |  |  | 2024-09-02 | Completed
1.2 | Create S3 access | BluSapphire |  |  | Akhila |  |  | 2024-09-02 | Completed
1.3 | Admin User Account creation | BluSapphire |  |  | Akhila |  |  | 2024-09-02 | Completed
1.4 | Adding Devices | BluSapphire |  |  | Akhila |  |  | 2024-09-02 | Completed
2 | Log Collector - Location 2 (Bangalore or Cochin) | Client & BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed
2.1 | Point of contact (at this Location) : Name & contact | Client |  |  | Akhila |  |  | 2024-09-19 | Completed
2.2 | Configuration Requirements (Basic): OS version: Rocky Linux 8.6 Minimal/Rocky Linux 8.7 Minimal only Hardware: vCPUs = 4 ; RAM = 8GB ; Disk space = 256 (min 200GB for '/opt' or '/' partition). | Client |  |  | Akhila |  |  | 2024-09-19 | Completed
2.3 | Is an Private Static IP address provisioned for the Log Collector(s), If so, specify the following for each Log Collector? | Client |  |  | Akhila |  |  | 2024-09-19 | Completed
2.4 | Is Internet provisioned on Log Collector during deployment activity? | Client |  |  | Akhila |  |  | 2024-09-19 | Completed
2.5 | Requested outbound ports to be opened on the firewall 5414, 5415 & 5416/udp to Master, BL ips and 443 port is opened | Client |  |  | Akhila |  |  | 2024-09-19 | Completed
2.6 | Installation of Log Collector software | Client/BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed |  | Dependency on 2.1 to 2.4
2.7 | Verification of Log Collector | Client/BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed |  | Dependency on 2.1 to 2.4
2.8 | Verify end to end connectivity with SaaS | Client/BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed |  | Dependency on 2.1 to 2.4
3 | Responder - Location 2 (Bangalore or Cochin) | Client & BluSapphire |  |  | Akhila |  |  | 2024-09-24
3.1 | Is an Private Static IP address provisioned for the Responder(s), If so, specify the following for each Responder machine? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.2 | Requested outbound ports to be opened on the firewall | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.3 | Is a service account created on AD for Responder machine with local admin privileges on endpoints? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.4 | Is WinRM setup in Group Policy on AD? And is responder machine part of WinRM client->trusted host list. | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.5 | Is the PowerShell version on Responder > 5.0? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.6 | Is the PowerShell version on all endpoints >= 3.0? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.7 | Is Responder and work-stations added in AD? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.8 | Is forward lookup and reverse lookup configured in active directory? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.9 | If there is any firewall running in workstations, need to enable inbound rule to allow WinRM and WMI. | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.10. | Is the Windows Firewall on Responder have the WinRM ports allowed? | Client |  |  | Akhila |  |  | 2024-09-24 | Completed
3.11 | Installation of Responder software | BluSapphire |  |  | Akhila |  |  | 2024-09-24 | Completed |  | Dependency on system requirements(H/W & S/W) and 5.1 & 5.4
3.12 | Configuration of Responder | BluSapphire |  |  | Akhila |  |  | 2024-09-24 | Completed |  | Dependency on 5.1 to 5.9
3.13 | Verification of Responder | BluSapphire |  |  | Akhila |  |  | 2024-09-24 | Completed |  | Dependency on 5.1 to 5.9
4 | MicroAgent Deployment at Windows End points | Client & BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed |  | Dependency on Log Collector
4.1 | MicroAgent build package and installation guide(GPO) to be provided | BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed
4.2 | Log forwarder (Winlogbeat) | Client/BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed
4.3 | Sysmon (Latest sysmon version to be downloaded from Microsoft Sysinternals website) | Client/BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed
4.4 | End to end communication check between MicroAgent & Log Collector | Client/BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed
5 | End to end integration test | BluSapphire |  |  | Akhila |  |  | 2024-09-19 | Completed |  | Dependency on 1 to 3
6 | Change Management Process If any | Client/BluSapphire

## Log Integration
S.No | Milestones and Deliverables | Owner | Type of Log Source/Device (Phoenix - PHX, HYD, Fremont & SMCI) | [7 empty] | Notes/Comments
|  |  | Windows logs (incl. Sysmon) | Linux | Palo Alto Firewall | Cloud-sophos central | cloud-aws | Cloud-cisco meraki | cloud- 0365 | Microsoft Azure AD
1 | No. of devices | Client
2 | Configuration information | BluSapphire | Port/Protocol: 12102/TCP | Port/Protocol: 12514/udp | Port/Protocol: 12208 | API | API | API | API | API
3 | In Scope | Client / BluSapphire | YES | YES | YES | YES | YES | YES | YES | YES
4 | Log forwarding (listening on specified port, Receive the data and forward to SaaS) | BluSapphire | Completed (26th September 2024) | Completed (27th September 2024) | Completed (26th September 2024) | Completed (3rd October 2024) | Completed (9th October 2024) | Completed (10th October 2024) | Completed (27th September 2024) | Completed (29th October 2024)
5 | Test machines (if any) | Client | NA | NA | NA | NA | NA | NA | NA | NA
6 | SIEM configuration changes | Client | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7 | Log Integration - Steps |  | Completed (26th September 2024) | Completed (27th September 2024) | Completed (26th September 2024) | Completed (3rd October 2024) | Completed (9th October 2024) | Completed (10th October 2024) | Completed (27th September 2024) | Completed (29th October 2024)
7.1 | Create/use existing parser | BluSapphire | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists
7.2 | Verify receipt of the logs | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.3 | Indexing | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.4 | Log normalization / validation | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.5 | Creating Dashboards (standard/basic) | BluSapphire | Completed (26th September 2024) | Completed (27th September 2024) | Completed (26th September 2024) | Completed (3rd October 2024) | Completed (9th October 2024) | Completed (10th October 2024) | Completed (27th September 2024) | Completed (29th October 2024)
8 | Use Cases/Rule implementation (standard/basic) | Client / BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
9 | Post initial scope completion (after PCR signoff) On-going process | Client / BluSapphire
9.1 | Rule/Environment Tuning - As required | Client / BluSapphire
9.2 | Custom dashboards - As required | Client / BluSapphire
9.3 | Adapting to client environment | Client / BluSapphire
9.4 | Whitelisting of known enterprise applications | Client / BluSapphire
9.5 | New log source integration - As required | Client / BluSapphire
S.No | Milestones and Deliverables | Owner | Type of Log Source/Device (Bangalore or Cochin) |  |  | Notes/Comments
|  |  | Windows logs | Linux | Fortigate Firewall
1 | No. of devices | Client
2 | Configuration information | BluSapphire | Port/Protocol: 12102/TCP | Port/Protocol: 12514/udp | Port/Protocol: 12293/udp
3 | In Scope | Client / BluSapphire | YES | YES | YES
4 | Log forwarding (listening on specified port, Receive the data and forward to SaaS) | BluSapphire | Completed (27th September 2024) | Completed (27th September 2024) | Completed (27th September 2024)
5 | Test machines | Client | Completed | Completed | NA
6 | SIEM configuration changes | Client | Completed | Completed | Completed
7 | Log Integration - Steps |  | Completed (27th September 2024) | Completed (27th September 2024) | Completed (27th September 2024)
7.1 | Create/use existing parser | BluSapphire | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists
7.2 | Verify receipt of the logs | BluSapphire | Completed | Completed | 1
7.3 | Indexing | BluSapphire | Completed | Completed | Completed
7.4 | Log normalization / validation | BluSapphire | Completed | Completed | Completed
7.5 | Creating Dashboards (standard/basic) | BluSapphire | Completed | Completed | Completed
8 | Use Cases/Rule implementation (standard/basic) | Client / BluSapphire | Completed | Completed | Completed
9 | Post initial scope completion (after PCR signoff) On-going process | Client / BluSapphire
9.1 | Rule/Environment Tuning - As required | Client / BluSapphire
9.2 | Custom dashboards - As required | Client / BluSapphire
9.3 | Adapting to client environment | Client / BluSapphire
9.4 | Whitelisting of known enterprise applications | Client / BluSapphire
9.5 | New log source integration - As required | Client / BluSapphire

## Client Details
Client name:Milestone
Project type: PROD
Partner (if any) | vcircuit
Solution opted | SIEM+TI+UEBA+NBAD+R&R
EPS / Storage (online) | 2500
Log Retention (cold storage) | 60 days Hot / Online
SOC managed by | Vcircuit
Location 1 | Phoenix - PHX, HYD, Fremont & SMCI
Location 2 | Bangalore, Cochin
Org code | 0dc864de
Location code (Sensor ID) 1 | MC_PH_S01 (phoenix),MC_HY_S01(Hyderabad),MC_FM_S01(Fremont)
Location code (Sensor ID) 2 | MC_KC_S01(Cochin)
Components deployed | IP
Master 1 | 68.183.59.195
Master 2 | 52.87.122.143
BL_IP 1 | 143.198.61.109
BL_IP 2 | 44.207.63.232
Log Collector 1 (private IP)
Responder (private IP)
|  | Sr.No | Log Source | Status | port / protocol | Integartion link
|  | 1 | Windows | Completed | 12102 / tcp | ​​Pheonix log integration​​ (This folder link contains details of all log source integrations)
|  | 2 | Firewall-paloalto | Completed | 12208 / udp
|  | 3 | Linux | Pending from Milestone | 12514 / udp
|  | 4 | Cloud-sophos central | Pending from Milestone | API
|  | 5 | Cloud-cisco meraki | Pending from Milestone | API
|  | 6 | cloud- 0365 | Pending from Milestone | API
|  | 7 | clous-aws | Pending from Milestone | API
|  | 8 | Microsoft Azure AD | Pending from Milestone | API | Microsoft Azure AD

## Inventory Location 1
NGFW (1) |  |  | Windows(45) |  |  | EDR(44) |  |  | Linux(1)
S.no. | Sensor id | Host / IP | S.no. | Sensor id | Host / IP | S.no. | Sensor id | Host / IP | S.no. | Sensor id | Host / IP
1 | MC_HY_S01 | phx-fw1a | 1 | MC_HY_S01 | phx-dc01 | 1 | MC_HY_S01 | phx-dc01 | 1 | MC_HY_S01 | 10.80.10.73
|  |  | 2 | MC_PN_S01 | MS-SQL01 | 2 | MC_PN_S01 | phx-fsm
[5 empty] | ms-dc05 |  |  | ms-exchange2019
[5 empty] | phx-dc02 |  |  | ms-win10-manas
[5 empty] | phx-fsm |  |  | ms-win10-shankar
[5 empty] | ms-azds01 |  |  | ms-win10-pramod
[5 empty] | ms-exchange2019 |  |  | ms-rapid7-ivm
[5 empty] | MS-SQL02 |  |  | ms-win10-neetha
[5 empty] | ms-bullhorn |  |  | ms-win10-supriya
[5 empty] | ms-win10-pramod |  |  | ms-win10-shyamraj
[5 empty] | HDQ-EDW-DEV |  |  | ms-win10-akanuganti
[5 empty] | ms-win10-manas |  |  | hdq-win10a
[5 empty] | ms-win10-neetha |  |  | ms-win10-venu
[5 empty] | ms-fcs01 |  |  | ms-adm01
[5 empty] | ms-adm01 |  |  | ms-dc05
[5 empty] | HDQ-EDW-PROCESS |  |  | ms-veeam
[5 empty] | hdq-winserver1 |  |  | phx-dc02
[5 empty] | ms-winserver3 |  |  | ms-azds01
[5 empty] | ms-win10-venu |  |  | MS-SQL02
[5 empty] | hdq-win10a |  |  | MS-SQL01
[5 empty] | phx-backup |  |  | hdq-winserver1
[5 empty] | ms-win10-supriya |  |  | ms-dtcentral
[5 empty] | phx-okta-radius |  |  | HDQ-EDW-DEV
[5 empty] | ms-okta-radius |  |  | ms-bullhorn
[5 empty] | ms-okta-radius02 |  |  | ms-winserver3
[5 empty] | phx-okta |  |  | ms-win10pro-a
[5 empty] | ms-win10-akanuganti |  |  | ms-win10pro-b
[5 empty] | ms-win10-shankar |  |  | HDQ-EDW-PROCESS
[5 empty] | ms-win10-shyamraj |  |  | ms-sftp
[5 empty] | hdq-billpro-dev |  |  | hdq-billpro-dev
[5 empty] | ms-win10pro-a |  |  | phx-okta
[5 empty] | ms-win10pro-b |  |  | phx-okta-radius
[5 empty] | ms-okta |  |  | ms-fcs01
[5 empty] | ms-veeam |  |  | ms-okta
[5 empty] | ms-workato-opa |  |  | ms-okta-radius02
[5 empty] | ms-rapid7-ivm |  |  | ms-okta-radius
[5 empty] | ms-sftp |  |  | ms-workato-opa
[5 empty] | ms-dtcentral |  |  | MS-WSUS
[5 empty] | MS-WSUS |  |  | phx-backup
[5 empty] | ms-win10-ankur |  |  | ms-win10-ankur
[5 empty] | hdq-win10c | 3 | MC_FM_S01 | HDQ-DC01
|  |  | 3 | MC_FM_S01 | HDQ-DC01 |  |  | ms-dc04
[5 empty] | ms-dc04 |  |  | HQ-OKTA-RADIUS
[5 empty] | HQ-OKTA-RADIUS |  |  | ms-print01
ms-print01

## Inventory Location 2
Windows(1) |  |  | EDR(4)
S.no. | Sensor id | Host / IP | S.no. | Sensor id | Host / IP
1 | MC_KC_S01 | MILCOKDC02 | 1 | MC_KC_S01 | MILCOKMSSQL01
|  | MILCOKDC01 |  |  | MILCOKDC02
|  | MILCOKMSSQL01 |  |  | MILCOKDC01
|  | MILCOKCVB01 |  |  | MILCOKCVB01

## Sheet1
Phoenix
S.No | Device type | Port | Status of log integration
1 | Windows logs | 12102/TCP | Completed (26th September 2024)
2 | Linux | 12514/udp | Completed (27th September 2024)
3 | Palo Alto Firewall | 12208/udp | Completed (26th September 2024)
4 | Cloud-sophos central | API | Completed (3rd October 2024)
5 | cloud- 0365 | API | Completed (27th September 2024)
6 | cloud-aws | API | Completed (9th October 2024)
7 | Cloud-cisco meraki | API | Completed (10th October 2024)
8 | Microsoft Azure AD | API | Pending
Cochin
S.No | Device type | Port | Status of log integration
1 | Windows logs | 12102/TCP | Completed (27th September 2024)
2 | Linux | 12514/udp | Completed (27th September 2024)
3 | Fortigate Firewall | 12293/udp | Pending