## Overall Status
Project Status - Client name
# | Milestones and Deliverables | Planned Date | Planned Duration | Actual start Date | Actual Duration | Completion date | % Done | Notes/Comments
1 | Project Kick-off meeting and Network Architecture Study | [5 empty] | 0%
2 | Follow up meeting - Project plan | [5 empty] | 0%
3 | Walkthrough and Pre-Deployment checklist Sign-off | [5 empty] | 0%
4 | Verify/confirm Pre-deployment checklist before proceeding with deployment | [5 empty] | 0%
5 | Deployment of BluSapphire Components | [5 empty] | 0%
6 | Log integration | [5 empty] | 0%
7 | Operational Dashboard (Basic/standard) | [5 empty] | 0%
8 | BluSapphire Platform Training | [5 empty] | 0%
9 | Environment Health Monitoring | [5 empty] | 0%
10 | Integration to Ticketing Tool (if any)
11 | PCR sign off (move to monitoring stage) | [5 empty] | 0%
12 | Post Production (On-going process) | [5 empty] | 0%
12.1 | Rule/Environment Tuning - As required | [5 empty] | 0%
12.2 | Custom dashboards - As required | [5 empty] | 0%
12.3 | New log source integration - As required | [5 empty] | 0%

## Deployment overview
S.No | Milestones and Deliverables | Owner | OS Version | Planned Date | Planned Duration | Resource Allocated | Actual start Date | Actual Duration | Completion date | Status | Agreed by Client | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  |  |  | Akhila |  |  | 2023-11-14 | Completed |  | Dependency on Pre-deployment checklist completion
2 | Gateway Collector | BluSapphire |  |  |  | Akhila |  |  | 2023-11-14 | Completed |  | Dependency on 1
3 | Log Collector | Client & BluSapphire | Rocky linux 8.6 minimal |  |  | Akhila |  |  | 2023-11-15 | Completed |  | Dependency on server availability with all pre-requisites fulfilled
4 | Responder | Client & BluSapphire | Windows server 2016 & above |  |  | Akhila |  |  | 2023-11-29 | Completed |  | Dependency on server availability with all pre-requisites fulfilled
5 | MicroAgent Deployment for windows machines at End points | Client & BluSapphire |  |  |  | Akhila |  |  | 2023-11-19 | Completed |  | Dependency on Log Collector
6 | End to end integration test | BluSapphire |  |  |  | Akhila |  |  | 2023-11-19 | Completed |  | Dependency on 1 to 6
7 | BluHeraldry Deployment | BluSapphire |  |  |  | Akhila |  |  | Monday, 20 November, 2023 | Completed |  | Dependency on Logs integration
8 | Change Management Process If any | Client/BluSapphire

## Deployment details
S.No | Milestones and Deliverables | Owner | Planned Date | Planned Duration | Resource Allocated | Actual Start Date | Actual Duration | Completion date | Status | Agreed by Client | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
1.1 | Add Organisation | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
1.2 | Add spaces to ODP | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
1.3 | Admin User Account creation | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
1.4 | Adding Devices | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
2 | Gateway Collector | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
2.1 | Gateway Collector ZTN Deployment & Verification | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
2.2 | Gateway Collector Installation & Verification | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
2.3 | Gateway Collector Configuration & Verification | BluSapphire |  |  | Akhila |  |  | 2023-11-14 | Completed
3 | Log Collector | Client & BluSapphire |  |  | Akhila |  |  | 2023-11-15 | Completed
3.1 | Is an Private Static IP address provisioned for the Log Collector(s), If so, specify the following for each Log Collector? | Client |  |  | Akhila |  |  | 2023-11-15 | Completed
3.2 | Is Internet provisioned on Log Collector during deployment activity? | Client |  |  | Akhila |  |  | 2023-11-15 | Completed
3.3 | Requested outbound ports to be opened on the firewall | Client |  |  | Akhila |  |  | 2023-11-15 | Completed
3.4 | Installation of Log Collector software | Client/BluSapphire |  |  | Akhila |  |  | 2023-11-15 | Completed
3.5 | Verification of Log Collector | Client/BluSapphire |  |  | Akhila |  |  | 2023-11-15 | Completed
3.6 | Verify end to end connectivity with corresponding GW-Collector | Client/BluSapphire |  |  | Akhila |  |  | 2023-11-15 | Completed
4 | Responder | Client & BluSapphire |  |  | Akhila |  |  | 2023-11-29 | Completed
4.1 | Is an Private Static IP address provisioned for the Responder(s), If so, specify the following for each Responder machine? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.2 | Requested outbound ports to be opened on the firewall | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.3 | Is a service account created on AD for Responder machine with local admin privileges on endpoints? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.4 | Is WinRM setup in Group Policy on AD? And is responder machine part of WinRM client->trusted host list. | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.5 | Is the PowerShell version on Responder > 5.0? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.6 | Is the PowerShell version on all endpoints >= 3.0? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.7 | Is Responder and work-stations added in AD? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.8 | Is forward lookup and reverse lookup configured in active directory? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.9 | If there is any firewall running in workstations, need to enable inbound rule to allow WinRM and WMI. | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.10. | Is the Windows Firewall on Responder have the WinRM ports allowed? | Client |  |  | Akhila |  |  | 2023-11-29 | Completed
4.11 | Installation of Responder software | BluSapphire |  |  | Akhila |  |  | 2023-11-29 | Completed |  | Dependency on system requirements(H/W & S/W) and 5.1 & 5.4
4.12 | Configuration of Responder | BluSapphire |  |  | Akhila |  |  | 2023-11-29 | Completed |  | Dependency on 5.1 to 5.9
4.13 | Verification of Responder | BluSapphire |  |  | Akhila |  |  | 2023-11-29 | Completed |  | Dependency on 5.1 to 5.9
5 | MicroAgent Deployment at Windows End points | Client & BluSapphire |  |  | Akhila |  |  | 2023-11-19 | Completed |  | Dependency on Log Collector
5.1 | MicroAgent build package and installation guide(GPO) to be provided | BluSapphire |  |  | Akhila |  |  | 2023-11-19 | Completed
5.2 | Log forwarder (Winlogbeat) | Client/BluSapphire |  |  | Akhila |  |  | 2023-11-19 | Completed
5.3 | End to end communication check between MicroAgent & Log Collector | Client/BluSapphire |  |  | Akhila |  |  | 2023-11-19 | Completed
6 | End to end integration test | BluSapphire |  |  | Akhila |  |  | 2023-11-19 | Completed |  | Dependency on 1 to 6
7 | BluHeraldry deployment | BluSapphire |  |  | Akhila |  |  | 2023-11-20 | Completed |  | Dependency on Logs integration
8 | Change Management Process If any | Client/BluSapphire

## Log Integration
S.No | Milestones and Deliverables | Owner | Type of Log Source/Device | [17 empty] | Notes/Comments
|  |  | Windows logs | [5 empty] | Cisco Switch | [5 empty] | DNS/DHCP
| Location |  | PPHS | SUNRISE | COOPER | PINES | BOYNTON | PBG | PPHS | SUNRISE | COOPER | PINES | BOYNTON | PBG | PPHS | SUNRISE | COOPER | PINES | BOYNTON | PBG
1 | No. of devices | Client
2 | Configuration information | BluSapphire | Port/Protocol: 12102/TCP | Port/Protocol: 12102/TCP | Port/Protocol: 12102/TCP | Port/Protocol: 12102/TCP | Port/Protocol: 12102/TCP | Port/Protocol: 12102/TCP | Port/Protocol: | Port/Protocol: | Port/Protocol: | Port/Protocol: | Port/Protocol: | Port/Protocol: 12515/udp | Port/Protocol: 12202/tcp | Port/Protocol: 12202/tcp | Port/Protocol: 12202/tcp | Port/Protocol: 12202/tcp | Port/Protocol: 12202/tcp | Port/Protocol: 12202/tcp
3 | In Scope | Client / BluSapphire | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
4 | Log forwarding (listening on specified port, Receive the data and forward to GW Collector) | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
5 | Test machines | Client | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS | Provided by BluS
6 | SIEM configuration changes | Client | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7 | Log Integration - Steps |  | Completed (19 November 2023) | Completed | Completed | Completed | Completed | Completed | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed | Completed | Completed | Completed | Completed | Completed
7.1 | Create/use existing parser | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.2 | Verify receipt of the logs | BluSapphire | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists
7.3 | Indexing | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.4 | Log normalization / validation | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.5 | Data enrichment | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7.6 | Corelation of logs | BluSapphire | Completed (19 November 2023) |  | Completed | Completed | Completed | Completed | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed | Completed | Completed | Completed | Completed | Completed
7.7 | Visualization for logs | BluSapphire | Completed (19 November 2023) |  | Completed | Completed | Completed | Completed | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed | Completed | Completed | Completed | Completed | Completed
7.8 | Creating Dashboards (standard/basic) | BluSapphire | Completed (19 November 2023) |  | Completed | Completed | Completed | Completed | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed (10 December 2023) | Completed | Completed | Completed | Completed | Completed | Completed
8 | Use Cases/Rule implementation (standard/basic) | Client / BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed |  |  |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
9 | Post initial scope completion (after PCR signoff) On-going process | Client / BluSapphire
9.1 | Rule/Environment Tuning - As required | Client / BluSapphire
9.2 | Custom dashboards - As required | Client / BluSapphire
9.3 | Adapting to client environment | Client / BluSapphire
9.4 | Whitelisting of known enterprise applications | Client / BluSapphire
9.5 | New log source integration - As required | Client / BluSapphire