## Overall status
Project Status - Kiya.ai (Phase 1)
# | Milestones and Deliverables | Planned Date | Planned Duration | Actual start Date | Actual Duration | Completion date | % Done | Notes/Comments
1 | Project Kick-off meeting and Network Architecture Study |  |  |  |  | 2023-06-15 | 100%
2 | Follow up meeting - Project plan |  |  |  |  | 2023-06-15 | 100%
3 | Walkthrough and Pre-Deployment checklist Sign-off |  |  |  |  | 2023-06-15 | 100%
4 | Verify/confirm Pre-deployment checklist before proceeding with deployment |  |  |  |  | 2023-06-15 | 100%
5 | Deployment of BluSapphire Components (DC) |  |  |  |  | 2023-06-26 | 90% | SPAN Configuration is pending from Kiya's end.
6 | Deployment of BluSapphire Components (DR) |  |  |  |  | 2023-08-17 | 90% | SPAN Configuration is pending from Kiya's end.
7 | Log integration (DC) |  |  |  |  | 2023-06-30 | 95% | Completed integration for UAT Server and Kiya Team is yet to provide access for PROD DB servers.
8 | Log integration (DR) |  |  |  |  | 2023-08-26 | 95% | Completed integration for UAT Server and Kiya Team is yet to provide access for PROD DB servers.
9 | Operational Dashboard (Basic/standard) (DC) |  |  |  |  | 2023-07-04 | 100%
10 | Operational Dashboard (Basic/standard) (DR) |  |  |  |  | 2023-08-28 | 100%
11 | BluSapphire Platform Training |  |  |  |  | 2023-08-18 | 100% | Session was attended by Anoop, Ashish, Akash & other team members of Kiya
12 | Environment Health Monitoring |  |  |  |  | 2023-08-18 | 100%
14 | Project Closure Report sign off (move to monitoring stage) | [5 empty] | 0%
15 | Handover to SecOps for monitoring |  |  |  |  | 2023-07-10 | 100% | Despite Implementation Project is due for completion, SecOps has commenced on 10th July'23 and is ongoing.
16 | Post Production (On-going process) | [5 empty] | 0%
16.1 | Rule/Environment Tuning - As required | [5 empty] | 0%
16.2 | Custom dashboards - As required | [5 empty] | 0%
16.3 | New log source integration - As required | [5 empty] | 0%

## Deployment overview
Deployment Overview-Prod_Navi Mumbai - DC
S.No | Milestones and Deliverables | Owner | OS Version | Planned Date | Planned Duration | Resource Allocated | Actual start Date | Actual Duration | Completion date | Status | Agreed by Client | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  |  |  | Akhila |  |  | 2023-06-15 | Completed |  | Dependency on Pre-deployment checklist completion
2 | Gateway Collector_Prod | BluSapphire |  |  |  | Akhila |  |  | 2023-06-15 | Completed |  | Dependency on 1
3 | Sensor - Navi Mumbai | Client & BluSapphire | Rocky linux 8.6 minimal |  |  | Akhila |  |  | 2023-06-27 | Completed |  | SPAN configuration is pending from the Client end. Dependency on server availability with all pre-requisites fulfilled
4 | Log Collector - Navi Mumbai | Client & BluSapphire | Rocky linux 8.6 minimal |  |  | Akhila |  |  | 2023-06-26 | Completed |  | Dependency on server availability with all pre-requisites fulfilled
5 | Responder - Navi Mumbai | Client & BluSapphire | Windows server 2016 & above |  |  | Akhila |  |  | 2023-06-28 | Completed |  | Dependency on server availability with all pre-requisites fulfilled
6 | MicroAgent Deployment for windows machines at End points | Client & BluSapphire |  |  |  | Akhila |  |  | 2023-06-27 | Completed |  | Dependency on Log Collector
7 | End to end integration test | BluSapphire |  |  |  | Akhila |  |  | 2023-07-04 | Completed |  | Dependency on 1 to 6
8 | BluHeraldry Deployment | BluSapphire |  |  |  | Akhila |  |  | 2023-07-05 | Completed |  | Dependency on Logs integration
Deployment Overview-Prod_Bengaluru - DR
S.No | Milestones and Deliverables | Owner | OS Version | Planned Date | Planned Duration | Resource Allocated | Actual start Date | Actual Duration | Completion date | Status | Agreed by Client | Notes/Comments
1 | Client Onboard - SaaS | BluSapphire |  |  |  | NA |  |  | NA | Completed |  | Same SaaS instance as DC
2 | Gateway Collector_Prod | BluSapphire |  |  |  | NA |  |  | NA | Completed |  | Same SaaS instance as DC
3 | Log Collector - Bengaluru | Client & BluSapphire | Rocky linux 8.6 minimal |  |  | Praveen |  |  | 2023-08-17 | Completed
3 | Sensor - Bengaluru | Client & BluSapphire | Rocky linux 8.6 minimal |  |  | Akhila |  |  | 2023-09-11 | Completed |  | SPAN configuration is pending from the Client end. Dependency on server availability with all pre-requisites fulfilled
5 | Responder - Bengaluru | Client & BluSapphire | Windows server 2016 & above |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on server availability with all pre-requisites fulfilled
4 | MicroAgent Deployment for windows machines at End points | Client & BluSapphire |  |  |  | Akhila |  |  | 2023-08-29 | Completed |  | Shared to Kiya
5 | End to end integration test | BluSapphire |  |  |  | Akhila |  |  | 2023-08-29 | Completed
8 | BluHeraldry Deployment | BluSapphire |  |  |  | Praveen |  |  | 2023-08-29 | Completed |  | Dependency on Logs integration

## Deployment details
S.No | Milestones and Deliverables | Owner | Planned Date | Planned Duration | Resource Allocated | Actual Start Date | Actual Duration | Completion date | Status | Agreed by Kiya | Notes/Comments
1 | Kiya Onboard - SaaS | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
1.1 | Add Organisation | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
1.2 | Add spaces to ODP | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
1.3 | Admin User Account creation | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
1.4 | Adding Devices | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
2 | Gateway Collector - DC Location | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
2.1 | Gateway Collector ZTN Deployment & Verification | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
2.2 | Gateway Collector Installation & Verification | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
2.3 | Gateway Collector Configuration & Verification | BluSapphire |  |  | Akhila |  |  | 2023-06-15 | Completed
3 | Sensor - DC Location | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
3.1 | Has a Private Static IP address been provisioned for the Sensor(s)? Please provide details | Kiya |  |  | Akhila |  |  | 2023-06-27 | Completed
3.2 | Is the sensor configured on the domain with a specified DNS name? If so, please provide the hostname to be used for the Sensor. | Kiya |  |  | Akhila |  |  | 2023-06-27 | Completed
3.3 | Is the SPAN/ Port Mirror configured? | Kiya |  |  | Akhila |  |  | 2023-06-27 | Completed
3.4 | Please specify the internal subnets (scope) | Kiya |  |  | Akhila |  |  | 2023-06-27 | Completed
3.5 | Requested outbound ports to be opened on the firewall | Kiya |  |  | Akhila |  |  | 2023-06-27 | Completed
3.6 | Installation of Sensor software | BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
3.7 | Verification of Sensor | BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
3.8 | Verify whether corresponding GW-Collector is receiving the data. | BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed |  | Dependency on 3.1 to 3.6
3.9 | Verify communication with Master | BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed |  | Dependency on 3.1 to 3.6
3.10. | Sensor Configuration | BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed |  | Dependency on 3.1 to 3.6
4 | Log Collector - DC Location | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-06-26 | Completed
4.1 | Is an Private Static IP address provisioned for the Log Collector(s), If so, specify the following for each Log Collector? | Kiya |  |  | Akhila |  |  | 2023-06-26 | Completed
4.2 | Is Internet provisioned on Log Collector during deployment activity? | Kiya |  |  | Akhila |  |  | 2023-06-26 | Completed
4.3 | Requested outbound ports to be opened on the firewall | Kiya |  |  | Akhila |  |  | 2023-06-26 | Completed
4.4 | Installation of Log Collector software | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-06-26 | Completed
4.5 | Verification of Log Collector | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-06-26 | Completed
4.6 | Verify end to end connectivity with corresponding GW-Collector | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-06-26 | Completed
5 | Responder - DC Location | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-06-28 | Completed
5.1 | Is an Private Static IP address provisioned for the Responder(s), If so, specify the following for each Responder machine? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.2 | Requested outbound ports to be opened on the firewall | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.3 | Is a service account created on AD for Responder machine with local admin privileges on endpoints? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.4 | Is WinRM setup in Group Policy on AD? And is responder machine part of WinRM Kiya->trusted host list. | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.5 | Is the PowerShell version on Responder > 5.0? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.6 | Is the PowerShell version on all endpoints >= 3.0? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.7 | Is Responder and work-stations added in AD? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.8 | Is forward lookup and reverse lookup configured in active directory? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.9 | If there is any firewall running in workstations, need to enable inbound rule to allow WinRM and WMI. | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.10. | Is the Windows Firewall on Responder have the WinRM ports allowed? | Kiya |  |  | Akhila |  |  | 2023-06-28 | Completed
5.11 | Installation of Responder software | BluSapphire |  |  | Akhila |  |  | 2023-06-28 | Completed |  | Dependency on system requirements(H/W & S/W) and 5.1 & 5.4
5.12 | Configuration of Responder | BluSapphire |  |  | Akhila |  |  | 2023-06-28 | Completed |  | Dependency on 5.1 to 5.9
5.13 | Verification of Responder | BluSapphire |  |  | Akhila |  |  | 2023-06-28 | Completed |  | Dependency on 5.1 to 5.9
6 | MicroAgent Deployment at Windows End points | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed |  | Dependency on Log Collector
6.1 | MicroAgent build package and installation guide(GPO) to be provided | BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
6.2 | Log forwarder (Winlogbeat) | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
6.3 | Sysmon (Latest sysmon version to be downloaded from Microsoft Sysinternals website) | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
6.4 | End to end communication check between MicroAgent & Log Collector | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-06-27 | Completed
7 | End to end integration test | BluSapphire |  |  | Akhila |  |  | 2023-07-04 | Completed |  | Dependency on 1 to 6
8 | BluHeraldry deployment | BluSapphire |  |  | Akhila |  |  | 2023-07-05 | Completed |  | Dependency on Logs integration
9 | Change Management Process If any | Kiya/BluSapphire
10 | Log Collector - DR Location | Kiya & BluSapphire |  |  | Praveen |  |  | 2023-08-17 | Completed
10.1 | Is an Private Static IP address provisioned for the Log Collector(s), If so, specify the following for each Log Collector? | Kiya |  |  | Praveen |  |  | 2023-08-17 | Completed
10.2 | Is Internet provisioned on Log Collector during deployment activity? | Kiya |  |  | Praveen |  |  | 2023-08-17 | Completed
10.3 | Requested outbound ports to be opened on the firewall | Kiya |  |  | Praveen |  |  | 2023-08-17 | Completed
10.4 | Installation of Log Collector software | Kiya/BluSapphire |  |  | Praveen |  |  | 2023-08-17 | Completed
10.5 | Verification of Log Collector | Kiya/BluSapphire |  |  | Praveen |  |  | 2023-08-17 | Completed
10.6 | Verify end to end connectivity with corresponding GW-Collector | Kiya/BluSapphire |  |  | Praveen |  |  | 2023-08-17 | Completed
11 | Sensor - DR Location | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed
11.1 | Has a Private Static IP address been provisioned for the Sensor(s)? Please provide details | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
11.2 | Is the sensor configured on the domain with a specified DNS name? If so, please provide the hostname to be used for the Sensor. | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
11.3 | Is the SPAN/ Port Mirror configured? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
11.4 | Please specify the internal subnets (scope) | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
11.5 | Requested outbound ports to be opened on the firewall | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
11.6 | Installation of Sensor software | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed
11.7 | Verification of Sensor | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed
11.8 | Verify whether corresponding GW-Collector is receiving the data. | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on 3.1 to 3.6
11.9 | Verify communication with Master | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on 3.1 to 3.6
11.10. | Sensor Configuration | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on 3.1 to 3.6
12 | Responder - DR Location | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed
12.1 | Is an Private Static IP address provisioned for the Responder(s), If so, specify the following for each Responder machine? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.2 | Requested outbound ports to be opened on the firewall | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.3 | Is a service account created on AD for Responder machine with local admin privileges on endpoints? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.4 | Is WinRM setup in Group Policy on AD? And is responder machine part of WinRM Kiya->trusted host list. | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.5 | Is the PowerShell version on Responder > 5.0? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.6 | Is the PowerShell version on all endpoints >= 3.0? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.7 | Is Responder and work-stations added in AD? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.8 | Is forward lookup and reverse lookup configured in active directory? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.9 | If there is any firewall running in workstations, need to enable inbound rule to allow WinRM and WMI. | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.10. | Is the Windows Firewall on Responder have the WinRM ports allowed? | Kiya |  |  | Akhila |  |  | 2023-09-11 | Completed
12.11 | Installation of Responder software | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on system requirements(H/W & S/W) and 5.1 & 5.4
12.13 | Configuration of Responder | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on 5.1 to 5.9
12.14 | Verification of Responder | BluSapphire |  |  | Akhila |  |  | 2023-09-11 | Completed |  | Dependency on 5.1 to 5.9
11 | MicroAgent Deployment at Windows End points | Kiya & BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed |  | Dependency on Log Collector
11.1 | MicroAgent build package and installation guide(GPO) to be provided | BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed
11.2 | Log forwarder (Winlogbeat) | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed
11.3 | Sysmon (Latest sysmon version to be downloaded from Microsoft Sysinternals website) | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed
11.4 | End to end communication check between MicroAgent & Log Collector | Kiya/BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed
12 | End to end integration test | BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed |  | Dependency on 1 to 6
13 | BluHeraldry deployment | BluSapphire |  |  | Akhila |  |  | 2023-08-29 | Completed |  | Dependency on Logs integration
14 | Change Management Process If any | Kiya/BluSapphire

## DC-Log Integration
S.No | Milestones and Deliverables | Owner | Type of Log Source/Device | [20 empty] | Notes/Comments
|  |  | Windows logs | Linux | Firewall Internal (ASA) | Load Balancer | Firewall DMZ/External (Firepower) | L2 Switches | Kaspersky Windows | Kaspersky Linux | L3 Switches | Routers | HyperVisor | DNS | VPNs | Tor Switches | SAN Switches | MSSQL | MYSQL | Oracle | FIM (Linux) | FIM (Window) | SPAN data
1 | No. of devices | Kiya | 39 | 90 | 2 | 4 | 2 | 4 | 38 | 68 | 2 | 2 | 20 | 4 | NA | 2 | 2 |  |  |  | 51 | 23
2 | Configuration information | BluSapphire | Method: Winlogbeat Agent Port/Protocol: 12102/TCP | Method: Linux Port/Protocol: 12514/udp | Port/Protocol: 12203/udp | Port/Protocol: 12323/udp | Port/Protocol: 12211/udp | Port/Protocol:12402/udp | Port/Protocol: 12407/udp | Port/Protocol: 12407/udp | Port/Protocol: 12403/udp | Port/Protocol: 12401/udp | Port/Protocol: 12325/udp | Port/Protocol: 12202/tcp | Port/Protocol: 12291/udp | Port/Protocol: 12405/udp | Port/Protocol:12404/udp | Port/Protocol:12326/udp | Port/Protocol:12326/udp | Port/Protocol:12326/udp | Port/Protocol:12418/udp | Method: Winlogbeat Agent Port/Protocol: 12102/TCP | 12101,12103 to 12106/tcp & 19001
3 | In Scope | Kiya / BluSapphire | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES
4 | Log forwarding (listening on specified port, Receive the data and forward to GW Collector) | BluSapphire | Completed (30 June 2023) | Completed (03 July 2023) | Completed (16th August 2023) | Completed (16th August 2023) (notes) | Completed (16th August 2023) | Completed (16 August 2023) | Completed (27th July 2023) | Completed (27th July 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (17th Aug 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (16 August 2023) | Completed (6th Dec 2023) | Completed (30 June 2023) | Completed (27th June 2023)
5 | Log integration from client end - supporting info / document / link | Kiya / BluSapphire | Provided by BluSapphire (27th June 2023) | Provided by BluSapphire (27th June 2023) | Provided by BluSapphire (24th July 2023) | NA | NA | NA | Provided by BluSapphire (24th July 2023) | Provided by BluSapphire (24th July 2023) | NA | Provided by BluSapphire on (24th July 2023) | Provided by BluSapphire on (4th September 2023) | Provided by BluSapphire on (24th July 2023) | Provided by BluSapphire on (30th August 2023) | Provided by BluSapphire on (24 July2023) | Provided by BluSapphire on (30th August 2023) | Provided by BluSapphire on (10 July2023) | Provided by BluSapphire on (10 July2023) | Provided by BluSapphire on (10 July2023) | Provided by BluSapphire on (7th Dec 2023) | Provided by BluSapphire on (24th Jan 2024) | Provided by BluSapphire on (27th June 2023)
6 | SIEM configuration changes | Kiya | Completed (30th June 2023) | Completed (02nd July 2023) | Completed (16th August 2023) | Completed (18th August 2023) | Completed (23rd August 2023) | Completed (24th August 2023) | Completed (26th July 2023) | Completed (26th July 2023) | Completed (29th August 2023) | Completed (8th August 23) | Completed (20 September 23) | Completed (18th Aug 2023) | Receiving through firewall | Completed (15 August 23) | Completed (11 Dec 23) | Integration for MSSQL is done for UAT server (10.10.7.11) KIYA team is yet to provide details for PROD DB servers. | Completed integration for UAT Server (10.10.5.16) and Kiya Team is yet to provide access for PROD DB servers. | Completed integration UAT Server (10.10.5.11) and Kiya Team is yet to provide access details for PROD DBs | Completed (19 Dec 23) | Completed (1 Feb 24) | SPAN Configuration is pending from Kiya's end.
7 | Log Integration - Steps | BluSapphire | Completed (04 July 2023) | Completed (04 July 2023) | Completed (18th August 2023) | Completed (19th August 2023) | Completed (24th August 2023) | Completed (24th August 2023) | Completed (27th July 2023) | Completed (27th July 2023) | Completed (29th August 2023) | Completed | Completed (21st September 2023) | Completed (19th August 2023) | NA | Completed (29th August 2023) | Completed |  |  |  | Completed (3rd November 2023) | Completed (1st Feb 2024)
7.1 | Verify receipt of the logs at GC | BluSapphire | Completed (30 June 2023) | Completed (03rd July 2023) | Completed (17th August 2023) | Completed (19 Aug 2023) | Completed (21 august 2023) | Completed (24th August 2023) | Completed (27th July 2023) | Completed (27th July 2023) | Completed (19th Aug 2023) | Completed (13th Aug 23) | Completed (14 August 23) | Completed (19th August 2023) | NA | Completed (15 August 23) | Though the configuration is in place, we are not receiving any logs. Kiya's team apprised that there is not much activitiy on this and hence the logs are not seen. |  |  |  | Completed ( 25th Jan 24) | Completed (1st Feb 2024)
7.2 | Create/use existing parser | BluSapphire | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Yes, New Parser has been created | Yes, Parser exists | NA | New Parser has been written | New Parser has been written |  |  |  | New Parser has been written | New Parser has been written
7.3 | Indexing | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | Completed |  |  |  | Completed | Completed
7.4 | Log normalization / validation | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | Completed |  |  |  | Completed | Completed
7.5 | Data enrichment | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | Completed |  |  |  | Completed | Completed
7.6 | Corelation of logs | BluSapphire | Completed (04 July 2023) | Completed (04th July 2023) | Completed (18th August 2023) | Completed (19th August 2023) | Completed (24th August 2023) | Completed (24th August 2023) | Completed (27th July 2023) | Completed (27th July 2023) | Completed (29 August 2023) | Completed (14th September 2023) | Completed (21 September 23) | Completed (19th August 2023) | NA | Completed | Completed |  |  |  | Completed | Completed
7.7 | Visualization for logs | BluSapphire | Completed (04 July 2023) | Completed (04 July 2023) | Completed (18th August 2023) | Completed (19th August 2023) | Completed (24th August 2023) | Completed (24th August 2023) | Completed (27th July 2023) | Completed (27th July 2023) | Completed (29 August 2023) | Completed (14th September 2023) | Completed (21 September 23) | Completed (19th August 2023) | NA | Completed | Completed |  |  |  | Completed | Completed
7.8 | Creating Dashboards (standard/basic) | BluSapphire | Completed (04 July 2023) | Completed (04 July 2023) | Completed (18th August 2023) | Completed (19th August 2023) | Completed (24th August 2023) | Completed (24th August 2023) | Completed (27th July 2023) | Completed (27th July 2023) | Completed (29 August 2023) | Completed (14th September 2023) | Completed (21 September 23) | Completed (19th August 2023) | NA | Completed | Completed |  |  |  | Completed | Completed
8 | Use Cases/Rule implementation (standard/basic) | Kiya / BluSapphire | Completed (05 July 2023) | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | Completed |  |  |  | Completed | Completed
9 | Post initial scope completion (after PCR signoff) | Client / BluSapphire
On-going process
9.1 | Rule/Environment Tuning - As required | Client / BluSapphire
9.2 | Custom dashboards - As required | Client / BluSapphire
9.3 | Adapting to client environment | Client / BluSapphire
9.4 | Whitelisting of known enterprise applications | Client / BluSapphire
9.5 | New log source integration - As required | Client / BluSapphire

## DR-Log Integration
S.No | Milestones and Deliverables | Owner | Type of Log Source/Device | [18 empty] | Notes/Comments
|  |  | Linux | Windows logs | HyperVisor | Firewall DMZ/External (Firepower) | Firewall Internal (ASA) | Kaspersky Windows | Kaspersky Linux | L3 Switches | Routers | San Switches | L2 Switches | Tor Switches | MSSQL | MYSQL | Oracle | VPNs | FIM (Linux) | FIM (Window) | SPAN data
1 | No. of devices | Kiya | 90 | 17 | 18 | 4 | 2 | 21 | 54 | 4 | 1 | 2 | 4 | 2 |  |  |  |  | 31 | 10
2 | Configuration information | BluSapphire | Method: Linux Port/Protocol: 12514/udp | Method: Winlogbeat Agent Port/Protocol: 12102/TCP | Port/Protocol:12325/udp | Port/Protocol:12211/udp | Port/Protocol:12203/udp | Port/Protocol: 12407/udp | Port/Protocol: 12323/udp | Port/Protocol:12403/udp | Port/Protocol:12401/udp | Port/Protocol:12404/udp | Port/Protocol:12402/udp | Port/Protocol:12405/udp | Port/Protocol:12326/udp | Port/Protocol:12326/udp | Port/Protocol:12326/udp | Port/Protocol:12291/udp | Port/Protocol:12418/udp | Method: Winlogbeat Agent Port/Protocol: 12102/TCP | 12101,12103 to 12106/tcp & 19001
3 | In Scope | Kiya / BluSapphire | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | YES
4 | Log forwarding (listening on specified port, Receive the data and forward to GW Collector) | BluSapphire | Completed (26th August 2023) | Completed (28th August 2023) | Completed (20th Sep 2023) | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed (16 August 2023) | Completed (16 August 2023) | Completed (16 August 2023) |  | Completed | Completed (30 June 2023) | Completed (11th Sept 2023)
5 | Log integration from Kiya end - supporting info / document / link | BluSapphire | Provided by BluSapphire (04th August 2023) | Provided by BluSapphire (04th August 2023) | Provided by BluSapphire (04th August 2023) | NA | NA | Provided by BluSapphire (24th July 2023) | NA | NA | Provided by BluSapphire (29th August 2023) | Provided by BluSapphire (29th August 2023) | NA | Provided by BluSapphire (29th August 2023) | Provided by BluSapphire on (10 July2023) | Provided by BluSapphire on (10 July2023) | Provided by BluSapphire on (10 July2023) | Provided by BluSapphire (29th August 2023) | Provided by BluSapphire on | Provided by BluSapphire on (24th Jan 2024) | Provided by BluSapphire on (27th June 2023)
6 | SIEM configuration changes | Kiya | Completed (26th August 2023) | Completed (28th August 2023) | Completed (20th Sep 2023) | Completed (26th Sep 2023) | Completed (26th Sep 2023) | Completed (6th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Complete 192.168.210.90 & 192.168.210.100 | Completed (29th Sep 2023) | Completed | Log integration for MSSQL for a UAT server (10.10.7.11) is done. KIYA team is yet to provide details for Prod DB servers. | Completed integration for a UAT Server (10.10.5.16) and Kiya Team is yet to provide access for PROD DBs. | Completed integration UAT Server (10.10.5.11) and Kiya Team is yet to provide access details for PROD DBs | Receiving through firewall | Completed | Completed (1 Feb 23) | SPAN Configuration is pending from Kiya's end.
7 | Log Integration - Steps |  | Completed (27th August 2023) | Completed (29th August 2023) | Completed (21st September 2023) | Completed (21st September 2023) | Completed (21st September 2023) | Completed (27th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed | Completed | Completed (29th August 2023) |  |  |  | NA | Completed (3rd November 2023) | Completed (1st Feb 2024)
7.1 | Verify receipt of the logs at GC | BluSapphire | Completed | Completed | Completed (20th Sep 2023) | Completed (26th Sep 2023) | Completed (26th Sep 2023) | Completed | Completed | Completed | Completed | Completed | Completed | Completed (15 August 23) |  |  |  | NA | Completed ( 23) | Completed (1 Feb 23)
7.2 | Create/use existing parser | BluSapphire | Yes, Parser exists | Yes, Parser exists | Yes, Parser exists | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | New Parser has been written |  |  |  | NA | New Parser has been written | New Parser has been written
7.3 | Indexing | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  |  | NA | Completed | Completed
7.4 | Log normalization / validation | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  |  | NA | Completed | Completed
7.5 | Data enrichment | BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  |  | NA | Completed | Completed
7.6 | Corelation of logs | BluSapphire | Completed | Completed | Completed (21st September 2023) | Completed (26th Sep 2023) | Completed (26th Sep 2023) | Completed (27th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed |  |  |  | NA | Completed | Completed
7.7 | Visualization for logs | BluSapphire | Completed (27th August 2023) | Completed (29th August 2023) | Completed (21st September 2023) | Completed (26th Sep 2023) | Completed (26th Sep 2023) | Completed (27th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed |  |  |  | NA | Completed | Completed
7.8 | Creating Dashboards (standard/basic) | BluSapphire | Completed (27th August 2023) | Completed (29th August 2023) | Completed (21st September 2023) | Completed (26th Sep 2023) | Completed (26th Sep 2023) | Completed (27th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed (29th Sep 2023) | Completed |  |  |  | NA | Completed | Completed
8 | Use Cases/Rule implementation (standard/basic) | Kiya / BluSapphire | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  |  | NA | Completed | Completed
9 | Post initial scope completion (after PCR signoff) | Kiya / BluSapphire
On-going process
9.1 | Rule/Environment Tuning - As required | Kiya / BluSapphire
9.2 | Custom dashboards - As required | Kiya / BluSapphire
9.3 | Adapting to Kiya environment | Kiya / BluSapphire
9.4 | Whitelisting of known enterprise applications | Kiya / BluSapphire
9.5 | New log source integration - As required | Kiya / BluSapphire

## Scope & Solution opted
Log Retention | 30 Days Online
Offered Solutions | SIEM, Threat Intelligence, UEBA, NTA-NBAD, EDR, Sandbox
Inventory of Production & Non Production as per SOW